## 332
TOOL NO :BM377 ERTH 400ml Rectangular Bottle HDPE M01 08-Cavity Mold BMU70E+ FN
S.NO | 3D modeling |  | COMPLETED
1 | MOLD DEVELOPMENT
2 | MOLD BASE PARTS
3 | ELECTRODE EXTRACTION
4 | MACHINING MODELS
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
1 | MOLD |  |  | Pravinya(18-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 1 | BODY INSERT- B |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 2 | BODY INSERT- P |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 3 | BASE INSERT- B |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 4 | BASE INSERT- P |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 5 | NECK INSERT B |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 6 | NECK INSERT P |  | Pravinya(19-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 7 | NECK INSERTMC |  | Mathew(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 8 | STRIKER INSERT- B |  | Mathew(16-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 9 | STRIKER INSERT- P* |  | Mathew(16-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 10 | SAND BLASTING SHEET
S.NO |  |  | 3D Development | Detailing | Verify |  | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
2 | MOLD BASE PARTS
| 1 | STRAP CLAMP* |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 2 | DISTANCE PIECE |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 3 | SUPPORT BLOCK |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 4 | DISTANCE PIN CUT OUT* |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 5 | DISTANCE PIN* |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 6 | WASHER@TL* |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 7 | BLOCKING WASHER* |  | Mathew(20-12-24) | kalyan |  | Mathew(20-12-24) | Mathew(20-12-24)
| 8 | INNER LEAK TESTING HEAD
| 9 | NECK INSERT EDM FIXTURE
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
4
1 | ASSEMBLY PARTING LINE DRAWING |  |  | Prema(23-12-24) | kalyan |  | Mathew(07-01-25) | Mathew(07-01-25)
2 | INSPECTION DRAWING |  |  | Prema(23-12-24) | kalyan |  | Mathew(07-01-25) | Mathew(07-01-25)
3 | CAVITY ENGRAVING
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
5 | MASK PARTS | [5 empty] | Prema(20-12-24) | Mathew(20-12-24)
| 1 | UPPER_PUNCH_MASK* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 2 | UPPER_MASK* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 3 | LOWER_PUNCH_MASK* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 4 | LOWER _MASK* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 5 | VACCUM_BAR_MASK* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 6 | STRIPPER_PLATE* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 7 | BASE_PUNCH* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 8 | BASE_PUNCH_DIST_PIN_100MM* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 9 | UPPER_SUPPORT_PLATE_T-O_ARM* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 10 | LOWER_SUPPORT_PLATE_T-O_ARM* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 11 | PUNCH_PLATE |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 12 | NECK_PUNCH_SHEET* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 13 | NECK_PUNCH_PART |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 14 | NECK_PART-P |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 15 | PUNCH DISTANCE BOLTS* |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 16 | PUNCH_LOCATING_BUSH |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
| 17 | VACCUMBAR_DISTANCE_BOLTS |  | Prema(20-12-24) | kalyan |  | Prema(20-12-24) | Mathew(20-12-24)
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
6 | ELECTRODES
ELECTRODE EXTRACTION
1 | E01 Groove Electrode
2 | E02 Full Thread
3 | E03 Thread start Elec
4 | E04 Thread end Elec
5
S.NO | Part list |  | Prepared | Verify |  | Released date |  | Submission/date | Rev | Additional Notes | Additional parts
1 | RAW MATERIAL PART LIST
2 | FINISHING SIZES PART LIST
3 | STARDARD PARTS PART LIST
4 | FASTERNS PART LIST
5 | ELECTRODES PART LIST
FILE SUBMISSION
CUSTOMER FILE SUBMISSION
| CHECK LIST |  |  | COMPLETED
2 | MOLD BASE PARTS
3 | MACHINING MODELS
4 | ELECTRODES
5 | FINISHING SIZES PART LIST
6 | STARDARD PARTS PART LIST