## 332
TOOL NO :BM454 Veedol 600ml M01 08Cavity SEB Mold SEB101 FN
S.NO | 3D MODELING |  |  | COMPLETED
1 | MOLD DEVELOPMENT |  |  | COMPLETED
2 | MOLD BASE PARTS
3 | ELECTRODE EXTRACTION
4 | MACHINING MODELS
S.NO |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date | 2D(Pdf)/date | Submission/date | Rev/date | Additional Notes | Additional parts
1 | MOLD |  |  | KALYAN | Swaraj
| 1 | BODY INSERT B |  | KALYAN | Swaraj
| 2 | BODY INSERT P |  | KALYAN
| 3 | BODY B WITH PINCH PLATE |  | KALYAN
| 4 | BODY P WITH PINCH PLATE |  | KALYAN
| 5 | Base Insert B |  | KALYAN | Rakesh
| 6 | Base Insert P |  | KALYAN | Rakesh
| 7 | Base Insert 8Deg angle fixture (date insert) |  | KALYAN
| 8 | BOTTOM INSERT- B |  | KALYAN | Swaraj
| 9 | BOTTOM INSERT- P |  | KALYAN | Swaraj
| 10 | NECK INSERT MC |  | KALYAN | Swaraj
| 11 | NECK INSERT B |  | KALYAN | Swaraj
| 12 | NECK INSERT P |  | KALYAN | Swaraj
| 13 | STRIKER INSERT B |  | KALYAN | Swaraj
| 14 | STRIKER INSERT P |  | KALYAN | Swaraj
| 15 | STRIKER INSERT BHT FIXTURE |  | KALYAN
| 16 | STRIKER INSERT AHT FIXTURE |  | KALYAN
| 17 | COOLING PLATE B |  | KALYAN
| 18 | COOLING PLATE P |  | KALYAN
| 19 | COOLING PLATE MC |  | KALYAN
| 20 | SAND BLASTING SHEET |  | KALYAN
S.NO |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date | 2D(Pdf)/date | Submission/date | Rev/date | Additional Notes | Additional parts
2 | MASK
| 1 | STRIPPER PLATE |  | KALYAN | swaraj/05.02.26
| 2 | UPPER MASK BUSH SIDE |  | KALYAN | swaraj/05.02.26
| 3 | LOWER MASK BUSH SIDE |  | KALYAN | swaraj/05.02.26
| 4 | UPPER MASK PIN SIDE |  | KALYAN | swaraj/05.02.26
| 5 | LOWER MASK PIN SIDE |  | KALYAN | swaraj/05.02.26
| 6 | NECK PART BUSH SIDE / PIN SIDE |  | KALYAN | swaraj/05.02.26
| 7 | MOUNTING PLATE -1(PARISON SIDE) |  | KALYAN | swaraj/05.02.26
| 8 | MOUNTING PLATE -2(TAKE OUT SIDE) |  | KALYAN | swaraj/05.02.26
| 9 | MOUNTING PUNCH PLATE |  | KALYAN | swaraj/05.02.26
| 10 | NECK PUNCH 1 |  | KALYAN | swaraj/05.02.26
| 11 | NECK PUNCH 2 |  | KALYAN | swaraj/05.02.26
| 12 | PUNCH DISTANCE BOLTS |  | KALYAN | swaraj/05.02.26
| 13 | COVERING SHEET (BENDING SHEET) |  | KALYAN | swaraj/05.02.26
| 14 | CONNECTING SHEET MASK ARM |  | KALYAN | swaraj/05.02.26
swaraj/05.02.26
S.NO |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date | 2D(Pdf)/date | Submission/date | Rev/date | Additional Notes | Additional parts
3 | MOLD BASE PARTS
| 1 | COOLING BLOCK |  |  | Rakesh/05.02.26
| 2 | STRAP CLAMPC
| 3 | SUPPORT BLOCK
| 4 | AIR DEFLECTOR SHEET
| 5 | DITANCE PIN /DISTANCE PIN WITH CUTOUT
| 6 | BLOCKING WASHER
| 7 | INNER LEAK TESTING HEAD
S.NO |  |  |  | 3D Development | Detailing/date | Verify/date |  | 2D(Pdf)/date | Submission/date
4
| 1 | ASSEMBLY PARTING LINE DRAWING
| 2 | INSPECTION DRAWING
| 3 | CAVITY ENGRAVING
S.NO |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date | 2D(Pdf)/date | Submission/date | Additional Notes
5 | ELECTRODE EXTRACTION
| 1 | E01 Groove Elec | E01 Groove Elec
| 2 | E02 Full Thread elec
| 3 | E03 Thread end elec
| 4 | E04_Snapper ring elec
| 5 | E06 Thread start elec-1
| 6 | E07 Thread start elec-2
| 7 | 20deg fixture for E07& R06
| 8 | E05-Logo electrode
S.NO | Part list |  |  | Prepared/date | Verify/date |  | Released/date |  | Submission/date | Additional Notes
2 | RAW MATERIAL PART LIST
3 | FINISHING SIZES PART LIST
4 | STARDARD PARTS PART LIST
5 | FASTERNS PART LIST
5 | ELECTRODES PART LIST
FILE SUBMISSION
CUSTOMER FILE SUBMISSION
| CHECK LIST |  |  |  | COMPLETED |  |  |  |  | Additional Notes
2 | MOLD BASE PARTS
3 | MACHINING MODELS
4 | ELECTRODES
5 | FINISHING SIZES PART LIST
6 | STARDARD PARTS PART LIST