## 332
TOOL NO : BM471 60ml CN Bottle 10+10 cav Mold Samsung90D CN
S.NO | 3D modeling |  | COMPLETED
1 | MOLD DEVELOPMENT |  | COMPLETED
2 | MOLD BASE PARTS |  | COMPLETED
3 | ELECTRODE EXTRACTION |  | COMPLETED
4 | MACHINING MODELS |  | COMPLETED
S.NO |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date | 2D(Pdf)/date | Submission/date | Rev | Additional Notes | Additional parts
1 | MOLD
| 1 | Back Plate BL/BR | A.Kalyan | yogendra/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2026
| 2 | Back Plate PL/PR | A.Kalyan | Ayppa/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2027
| 3 | Body Insert BL/BR | A.Kalyan | yogendra/26-03-2026 | Kalyan/28-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2028 | Swaraj/28-03-2026
| 4 | Body Insert PL/PR | A.Kalyan | yogendra/26-03-2026 | Kalyan/28-03-2027 | Yogendra/31-03-2026 | Yogendra/31-03-2029 | Swaraj/28-03-2027
| 5 | Base Insert BL/BR | A.Kalyan | Ayppa/26-03-2026 | Kalyan/28-03-2028 | Yogendra/31-03-2026 | Yogendra/31-03-2030 | Swaraj/28-03-2028
| 6 | Base Insert PL/PR | A.Kalyan | Ayppa/26-03-2026 | Kalyan/28-03-2029 | Yogendra/31-03-2026 | Yogendra/31-03-2031 | Swaraj/28-03-2029
| 7 | Bottom Insert BL/BR | A.Kalyan | yogendra/27-03-2026 | Kalyan/28-03-2030 | Yogendra/31-03-2026 | Yogendra/31-03-2032 | Swaraj/28-03-2030
| 8 | Bottom Insert PL/PR | A.Kalyan | yogendra/27-03-2026 | Kalyan/28-03-2031 | Yogendra/31-03-2026 | Yogendra/31-03-2033 | Swaraj/28-03-2031
| 9 | Neck Insert BL/BR | A.Kalyan | Ayppa/26-03-2026 | Kalyan/28-03-2032 | Yogendra/31-03-2026 | Yogendra/31-03-2034 | Swaraj/28-03-2032
| 10 | Neck Insert PL/PR | A.Kalyan | Ayppa/26-03-2026 | Kalyan/28-03-2033 | Yogendra/31-03-2026 | Yogendra/31-03-2035 | Swaraj/28-03-2033
| 11 | Neck Insert MC L/R | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2034 | Yogendra/31-03-2026 | Yogendra/31-03-2036 | Swaraj/28-03-2034
| 12 | Striker Insert BL/BR | A.Kalyan | Ayppa/27-03-2026
| 13 | Striker Insert PL/PR | A.Kalyan | Ayppa/27-03-2026
| 14 | Sand Blasting Sheet | A.Kalyan | A.Kalyan/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2039
| 15 | Neck Insert mc Fixture
| 16 | Neck Insert EDM fixture | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/28-03-2039 | Yogendra/31-03-2026 | Yogendra/31-03-2041 | Swaraj/28-03-2039
| 17 | striker Insert Turning Fixture | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/28-03-2040 | Yogendra/31-03-2026 | Yogendra/31-03-2042 | Swaraj/28-03-2040
| 18 | striker Insert Vertical Fixture |  | A.Kalyan/31-03-2046 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2043
| 19 | Striker Insert AHT Fixture
| 20 | Striker Insert BHT Fixture
| 21 | ASSEMBLY PARTING LINE DRAWING |  | A.Kalyan/31-03-2046 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/31-03-2046
| 22 | INSPECTION DRAWING |  | A.Kalyan/31-03-2046 | Kalyan/31-03-2026 |  | A.Kalyan/31-03-2046
| 23 | CAVITY ENGRAVING | Yogendra
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
2 | Mask PARTS
| 1 | Mask Back Plate BL/BR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2040 | Yogendra/31-03-2026 | Yogendra/31-03-2043 | Swaraj/28-03-2040
| 2 | Mask Back Plate PL/PR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2041 | Yogendra/31-03-2026 | Yogendra/31-03-2044 | Swaraj/28-03-2041
| 3 | Upper Mask BL/BR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2042 | Yogendra/31-03-2026 | Yogendra/31-03-2045 | Swaraj/28-03-2042
| 4 | Upper Mask PL/PR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2043 | Yogendra/31-03-2026 | Yogendra/31-03-2046 | Swaraj/28-03-2043
| 5 | Lower Mask BL/BR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2044 | Yogendra/31-03-2026 | Yogendra/31-03-2047 | Swaraj/28-03-2044
| 6 | Lower Mask PL/PR | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2045 | Yogendra/31-03-2026 | Yogendra/31-03-2048 | Swaraj/28-03-2045
| 7 | Neck Punch-1 L/R | A.Kalyan | Ayppa/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2049
| 8 | Neck Punch-2 L/R | A.Kalyan | Ayppa/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2050
| 9 | neck Punch Plate L/R | A.Kalyan | Ayppa/27-03-2026 | Kalyan/28-03-2048 | Yogendra/31-03-2026 | Yogendra/31-03-2051 | Swaraj/28-03-2048
| 10 | Punch Distance Bolt L/R | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/28-03-2048 | Yogendra/31-03-2026 | Yogendra/31-03-2052 | Swaraj/28-03-2049
| 11 | Neck punch guide | A.Kalyan | A.Kalyan/31-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/31-03-2026
| 12 | Neck Punch
| 13 | Mask ass drawing
| 14 | Neck Punch Assm Drawing
| 15 | Blow Pin Tip
| 16 | Blow Pin Tip AHT
| 17 | Blow Pin Tip BHT
| 18 | Cutting Ring
| 19 | Cutting Ring AHT
| 20 | Cutting Ring BHT
| 21 | Cutting Ring Wire Cut
S.NO | P |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Rev | Additional Notes | Additional parts
3 | MOLD BASE PARTS
| 1 | SUPPORT BLOCK MC | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2026
| 2 | STRAP CLAMP L/R | A.Kalyan | Ayppa/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Ayppa/28-03-2026
| 3 | DEFLECTOR SHEET L | A.Kalyan | Ayppa/28-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Ayppa/28-03-2026
| 4 | DEFLECTOR SHEET R | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2026
| 5 | BLOCKING WASHER* | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2027
| 6 | DISTANCE PIN WITH CUT OUT -L & R | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2028
| 7 | DISTANCE PIN -L & R | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2029
| 8 | TONNAGE SUPPORT BLOCK BL/BR & PL/PR | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2030
| 9 | TONNAGE SUPPORT BLOCK P4 | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2031
| 10 | TAPPER LOCK WASHER (Mold & Mask) | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2032
| 11 | MOLD CLAMPING PLATE L/R | A.Kalyan | A.Kalyan/27-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | A.Kalyan/27-03-2033
| 12 | MOLD MASK CONNECTING PLATE L/R
| 13 | Mask Clamping Plate
S.NO |  |  | 3D Development | Detailing | Verify | 3D DTP | 2D(Pdf) | Submission/date | Additional Notes
4 | ELECTRODES
| 1 | E01 Full Thread elec | Yogendra | Yogendra/31-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2026
| 2 | E02 Thread Start elec | Yogendra | Yogendra/31-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2026
| 3 | E03 Thread end elec | Yogendra | Yogendra/31-03-2026 | Kalyan/31-03-2026 | Yogendra/31-03-2026 | Yogendra/31-03-2026
| S.NO | Part list | Prepared | Verify |  | Released date |  | Submission/date | Additional Notes
| 1 | RAW MATERIAL PART LIST | A.Kalyan | Kalyan/28-03-2026 |  | 2026-03-28 |  | 2026-03-28
| 2 | FINISHING SIZES PART LIST | Yogendra | Kalyan/28-03-2026 |  | 2026-03-28 |  | 2026-03-28
| 3 | STARDARD PARTS PART LIST | Yogendra | Kalyan/28-03-2026 |  | 2026-03-28 |  | 2026-03-28
| 4 | FASTERNS PART LIST | Yogendra | Kalyan/28-03-2026 |  | 2026-03-28 |  | 2026-03-28
| 5 | ELECTRODES PART LIST | A.Kalyan | Kalyan/31-03-2026 |  | 2026-03-31 |  | 2026-03-28
| 6 | FILE SUBMISSION | Swaraj /28-03-2026 |  |  | 2026-03-28 |  | 2026-03-28
| 7 | CUSTOMER FILE SUBMISSION
|  | CHECK LIST |  | COMPLETED |  |  |  |  | Additional Notes
| 1 | MOLD BASE PARTS
| 2 | MACHINING MODELS
| 3 | ELECTRODES
| 4 | FINISHING SIZES PART LIST
| 5 | STARDARD PARTS PART LIST