## 332
TOOL NO : BM476 Vancouver 600ml 06-Cavity Mold BMU 70E+ FN
S.NO | 3D MODELING |  |  |  | COMPLETED
1 | MOLD DEVELOPMENT |  |  |  | COMPLETED
2 | MOLD BASE PARTS |  |  |  | COMPLETED
3 | ELECTRODE EXTRACTION |  |  |  | COMPLETED
4 | MACHINING MODELS |  |  |  | COMPLETED
S.NO |  |  |  |  | 3D Development | Detailing/date | Verify/date | 3D Data prog/date | 2D DFX/date | PDF/date | Submission/date | Rev/date | Additional Notes | Additional parts
1 | MOLD
| 1 | BODY INSERT-B | BODY INSERT- BL | BODY INSERT- BL | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 2 | BODY INSERT-P | BODY INSERT- PL | BODY INSERT- PL | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 3 | BASE INSERT-B | BODY INSERT- BR | BODY INSERT- BR | Praveen | Ayyappa/02-06-2026 | kalyan/03-06-2026
| 4 | BASE INSERT-P | BODY INSERT- PR | BODY INSERT- PR | Praveen | Ayyappa/02-06-2026 | kalyan/03-06-2026
| 5 | NECK_INSERT- MC | BASE INSERT- BL | BASE INSERT- BL | Swaraj | Swaraj/02-06-2026 | kalyan/03-06-2026
| 6 | NECK INSERT B | BASE INSERT- PL | BASE INSERT- PL | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 7 | NECK INSERT-P | BASE INSERT- BR | BASE INSERT- BR | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 8 | STRIKER INSERT- B | BOTTOM INSERT- PL | BOTTOM INSERT- PL | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 9 | STRIKER INSERT- P | BOTTOM INSERT- BR | BOTTOM INSERT- BR | Praveen | Swaraj/02-06-2026 | kalyan/03-06-2026
| 10 | PINCH_PLATES-1_MC- B, P | BOTTOM INSERT- PR | BOTTOM INSERT- PR | Mathew | Swaraj/03-06-2026 | kalyan/03-06-2026
| 11 | PINCH_PLATES-2_MC- B, P | NECK_INSERT- BL,BR, PL & PR | NECK_INSERT- BL,BR, PL & PR | Mathew | Swaraj/03-06-2026 | kalyan/03-06-2026
| 12 | PINCH PLATE FIXTURE-1 B, P | DUMMY_INSERT- BL,BR, PL & PR | DUMMY_INSERT- BL,BR, PL & PR | Mathew | Swaraj/03-06-2026 | kalyan/03-06-2026
| 13 | 8H7 SCREW PLUGS(PINCH PLATES | PINCH_PLATES-2_MC- B, P | PINCH_PLATES-2_MC- B, P | A.Kalyan | Mathew/04-06-2026 | kalyan/03-06-2026
| 14 | SAND BLASTING SHEETEET | PINCH PLATE FIXTURE-1 B, P | PINCH PLATE FIXTURE-1 B, P | Mathew
S.NO |  |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date |  | 2D(Pdf)/date | Submission/date | Rev/date | Additional Notes | Additional parts
2 | MASK
| 1 | UPPER_PUNCH_MASK* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 2 | UPPER_MASK* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 3 | LOWER_PUNCH_MASK* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 4 | LOWER _MASK* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 5 | VACCUM_BAR_MASK* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 6 | STRIPPER_PLATE* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 7 | BASE_PUNCH* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 8 | BASE_PUNCH_DISTANCE_PIN_100MM* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 9 | UPPER_SUPPORT_PLATE_T-O_ARM* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 10 | LOWER_SUPPORT_PLATE_T-O_ARM* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 11 | PUNCH_PLATE |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 12 | NECK_PUNCH_SHEET* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 13 | NECK_PUNCH_PART |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 14 | PUNCH DISTANCE BOLTS* |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 15 | PUNCH_LOCATING_BUSH |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 16 | VACCUMBAR_DISTANCE_BOLTS |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
| 17 | NECK PART |  |  | Praveen | Ayyappa /02-06-2026 | kalyan/03-06-2026
S.NO |  |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date |  | 2D(Pdf)/date | Submission/date | Rev/date | Additional Notes | Additional parts
3 | MOLD BASE PARTS
| 1 | SUPPORTING BLOCK | SUPPORTING BLOCK | SUPPORTING BLOCK | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 2 | DISTANCE PIECE B & P | DISTANCE PIECE B & P | DISTANCE PIECE B & P | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 3 | STRAP CLAMP* | STRAP CLAMP* | STRAP CLAMP* | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 4 | BLOCKING WASHER* Mc Model | BLOCKING WASHER* Mc Model | BLOCKING WASHER* Mc Model | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 5 | WASHER@TL* | WASHER@TL* | WASHER@TL* | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 6 | DISTANCE PIN WITH CUT OUT* | DISTANCE PIN WITH CUT OUT* | DISTANCE PIN WITH CUT OUT* | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 7 | DISTANCE PIN* | DISTANCE PIN* | DISTANCE PIN* | Praveen | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 8 | INNER LEAK TESTING HEAD | INNER LEAK TESTING HEAD | INNER LEAK TESTING HEAD | Mathew | Mathew /04-06-2026 | kalyan/04-06-2026
| 9 | 8H7 SCREW PLUGS(PINCH PLATES) | 8H7 SCREW PLUGS(PINCH PLATES) | 8H7 SCREW PLUGS(PINCH PLATES) | Praveen | Mathew /04-06-2026 | kalyan/04-06-2026
| 10 | NECK INSERT ENGRAVING FIXTURE | NECK INSERT ENGRAVING FIXTURE | NECK INSERT ENGRAVING FIXTURE | Mathew | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 11 | NECK INSERT EDM FIXTURE | NECK INSERT EDM FIXTURE | NECK INSERT EDM FIXTURE | Mathew | Ayyappa /02-06-2026 | kalyan/04-06-2026
| 12 | BODY INSERT ENGRAVING TRAIL PIECE B | BODY INSERT ENGRAVING TRAIL PIECE B | BODY INSERT ENGRAVING TRAIL PIECE B | Mathew | Rakesh /03-06-2026 | kalyan/04-06-2026
| 13 | BODY INSERT ENGRAVING TRAIL PIECE P | BODY INSERT ENGRAVING TRAIL PIECE P | BODY INSERT ENGRAVING TRAIL PIECE P | Mathew | Rakesh /03-06-2026 | kalyan/04-06-2026
| 14 | BODY INSERT PINCH PLATE FIXTURE | BODY INSERT PINCH PLATE FIXTURE | BODY INSERT PINCH PLATE FIXTURE | Mathew | Swaraj/03-06-2026 | kalyan/04-06-2026
S.NO |  |  |  |  | 3D Development | Detailing/date | Verify/date |  |  | 2D(Pdf)/date | Submission/date
4
| 1 | ASSEMBLY PARTING LINE DRAWING |  |  | Praveen | Rakesh/03-06-2026 | kalyan/04-06-2026
| 2 | INSPECTION DRAWING |  |  | Praveen | Rakesh/03-06-2026 | kalyan/04-06-2026
| 3 | CAVITY ENGRAVING
S.NO |  |  |  |  | 3D Development | Detailing/date | Verify/date | 3D DTP/date |  | 2D(Pdf)/date | Submission/date | Additional Notes
5 | ELECTRODE EXTRACTION
| 1 | E01 Groove Electrode |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 2 | E02 Thread Start |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 3 | E03 Full Thread |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 4 | E04 Thread end |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 5 | E05 Full Thread |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 6 | E06_Notch_Elec |  |  | Rakesh | Rakesh/03-06-2026 | Praveen/04-06-2026
| 7 | E07_Notch_Elec |  |  | Rakesh | Ayyappa /04-06-2026 | Praveen/04-06-2026
| 8 | E08_Notch_Elec |  |  | Mathew | Ayyappa /04-06-2026 | Praveen/04-06-2026
| 9 | e09_logo_elec |  |  | Mathew | Ayyappa /04-06-2026 | Praveen/02-06-2026
S.NO | Part list |  |  |  | Prepared/date | Verify/date |  | Released/date |  |  | Submission/date | Additional Notes
1 | RAW MATERIAL PART LIST |  |  |  | Praveen/02-05-2026 | Kalyan/03-05-2026
2 | FINISHING SIZES PART LIST |  |  |  | Mathew/02-06-2026 | Praveen/03-06-2026
3 | STARDARD PARTS PART LIST |  |  |  | Mathew/02-06-2026 | Pravven/03-06-2026
4 | FASTERNS PART LIST |  |  |  | Mathew/02-06-2026 | Praveen/03-06-2026
5 | ELECTRODES PART LIST |  |  |  | Mathew/02-06-2026 | Praveen/03-06-2026
6 | FILE SUBMISSION
7 | CUSTOMER FILE SUBMISSION